## Implementation CoverSheet (hidden)
WRP Implementation Planning Template
| ID | Template | Description | Location
Key Templates
| 1 | Implementation Readiness Workbook | This includes the following tabs:
| 2 | Release Notes
3
4
5
6
7
8
9
10
Cutover Night Readiness Checklist
| 12 | Have all Code Merges been scheduled. Have there been any Production releases that require a code merge with the new release. |  | Vodafone | Monday | 2005-09-19 | o
| 13 | Have the holding pages been signed off and communicated to VIS |  | Sapient/VIS | Tuesday | 2005-09-20 | x
| 14 |  |  | VF/Sape | Thursday | 2005-09-22 | o
| 15 |  |  | VF/Sape | Thursday | 2005-09-22 | o
| 16 |  |  | VF/Sape | Thursday | 2005-09-22 | o
| 17 |  |  | VF/Sape | Thursday | 2005-09-22 | o
| 18 |  |  | VF/Sape | Thursday | 2005-09-22 | o
| 19 |  |  | Sapient | Wednesday | 2005-09-21 | o
| 20 |  |  | Sapient | Friday | 2005-09-23 | o
| 21 |  |  | Sapient | Friday | 2005-09-23 | o
| 22 |  |  | VF/Sape | Friday | 2005-09-23 | o
o
Key
| x | Milestone has been completed.
| o | Milestone date is due on current date.
| o | Milestone date is past due.

## Mid Level Plan (hidden)
Vodafone R3.1.1 Implementation Schedule (Mid Level)
|  | Week 3 |  |  |  |  | Week 2 |  |  |  |  | Week 1 |  |  |  |  | Week 0 |  |  |  |  | Week (1) |  |  |  |  | Week (2) |  |  |  |  | Week (3)
|  | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI
|  | 2006-02-20 | 2006-02-21 | 2006-02-22 | 2006-02-23 | 2006-02-24 | 2006-02-27 | 2006-02-28 | 2006-03-01 | 2006-03-02 | 2006-03-03 | 2006-03-06 | 2006-03-07 | 2006-03-08 | 2006-03-09 | 2006-03-10 | 2006-03-13 | 2006-03-14 | 2006-03-15 | 2006-03-16 | 2006-03-17 | 2006-03-20 | 2006-03-21 | 2006-03-22 | 2006-03-23 | 2006-03-24 | 2006-03-27 | 2006-03-28 | 2006-03-29 | 2006-03-30 | 2006-03-31 | 2006-04-03 | 2006-04-04 | 2006-04-05 | 2006-04-06 | 2006-04-07
Release 3.1.1 Implementation Planning
Release 3.1.1 Dress Rehearsal Schedule
Release 3.1.1 Cutover Schedule
Release 3.1.1 Post-Cutover Activities DRAFT
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
Phase III Req Complete
DB cleanup tasks identified
DB cleanup tasks identified
ICS domain responsibilities completed
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
System Testing
(All Domains)
POC
Z
Eval copy of 7.5 installed, environment configured
Code and configuration changes
(All Domains)
Upgrade Dev Env
Code & config changes complete
System test complete
Finalize deployment strategy
(All Domains) upgraded and live
M Ops Deliverables (VDSI - Chennai)
M Ops Deliverables (VDSI - Delhi)
D / W Ops Deliverables (VDSI team - Chennai)
D / W Ops Deliverables (Sapient team)
D / W Ops Deliverables (VDSI team - Delhi)
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
East CP Vrepair Design, Development, IT Testing, UAT
10659 Design (I&M,National OPS)
Oracle Upgrade Investigation & Requirements
Z
LOE complete
Z
Plan Complete &
Capacity Allocated
Planning & Scheduling
Informatica Upgrade Investigation & Requirements
Z
LOE complete
Planning & Scheduling
USS drop CP (troubles only)
USS drop iView (CP)
Vrep and NY,NE,NJ,VA,WV cleanup, analysis - Design, Dev, IT Testing, UAT
Static data update for PA,DE and analysis CP
Static data update and analysis PADE
USS drop Vrepair
(all regions)
Static data drop
Start Production Support
CP conversion complete
iView and NY,NE,NJ,VA,WV cleanup, analysis Design, Dev, IT Testing, UAT
USS drop iView
(all regions)
East iView for CP Design, Development, IT Testing, UAT
Release IV
Development Complete
Requirements/Design Complete
r
Plan Complete &
Capacity Allocated
Disk Space Allocation and STE Environment Setup
(Infrastructure Team - Frank Estremera)
Z
STE Environment Setup and Space Allocated
STE Environment Data Load and Configuration
Deployment Testing beginning with October Data Month Release
UAT
(All Domains)
Parallel
(All Domains)
Implement CCRs
(All Domains)
Prod Upgrade / Sniff Test
(All Domains)
System Testing
(East MR & PR)
Upgrade Dev Env
(East MR & PR)
Parallel
(East MR & PR)
Implement CCRs
(East MR & PR)
Prod Upgrade / Sniff Test
(East MR & PR)
UAT & Parallel complete
UAT & Parallel complete
Finalize deployment strategy
(East MR & PR) Upgraded and live
System test complete
Performance Testing beginning with October Data Month Release
MR/PR Performance (Contention) Investigation & Requirements
Z
LOE complete
Z
Capacity Allocated and Scheduled
Planning & Scheduling
Z
Plan Complete
PR Performance (CTAS) Investigation & Requirements
Z
LOE complete
Z
Capacity Allocated and Scheduled
Planning & Scheduling
DB cleanup tasks identified
USS drop
Phase I
EMR, EBI, WNP/CO/DU
Common Services
Database Archiving, File Archiving, File Management
Phase II
EPO, EOR, WOR, WMR, WPO/INT, WPR, WBI
Phase III
EPR, EASR, ENP/GE/OD, EOR
Execute - Source File archiving
(ongoing)
DM, FM Phase I Live
DW Phase I Live
STE Env. Ready
Phase II Live
DM, FM Phase III Live
DW Phase III Live
Req Closed with Infra team
Phase III Dev Complete
Phase III Design Complete
Phase II Dev Complete
Phase II Design Complete
Phase II Req Complete
Phase I Dev Complete
Phase I Design Complete
Phase I Req Complete
Verizon Checkpoint
Documentation Updates
Internal Review
Second Review
Final Review and Productionize
r
r
r
r
Z
Investigation & requirements complete
Z
STE Environment plan and capacity allocation complete
OR Performance (CTAS) Investigation & Requirements
Z
LOE complete
Z
Capacity Allocated and Scheduled
Planning & Scheduling
Live (09/17)
Development - I&M
IT Testing - I&M
Depl Testing - I&M
Finish matching for one month data
Development complete for I&M
USS drop for I&M
Development - National OPS
IT - Nat. OPs
Depl - Nat. Ops
Development complete for National OPS
USS drop for National OPS
Finish matching for one month data
Ramp up
Requirements Gathering
Design
Estimate for Implementation Done
Monitor Trending Results
Z
Final Metric Trending Templates
Create and test New users and disable old users on DEV
MSTR UID Cleanup complete
Z
Z
Z
MSTR UID Cleanup on DEV complete
Phase 1 Design
Phase 1 Implementation
Phase 1 Testing
Phase 2 Design
Prod. Cleanup
MSTR UID Cleanup on Prod. complete
Create New Users on NT1 and NT3 machines and disable old users
Static Data Drop
Validation of PAD VRepair Conversion
IView Conversion complete
October
DB cleanup tasks identified
DB cleanup tasks identified
Execute - File Archiving
Execute DB Archiving - EMR, EBI, WBI, EPO, EPR, WMR, WPR
Source Files Archived
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
ASCII/Raw Data Files Archived
West BI
STG/DW/Mart Archived
DB cleanup tasks identified
DB cleanup tasks identified
East BI / PO
STG/Mart Archived
East MR/PR
Mart Archived
West PO/INT
STG/DW/ Mart Archived
Parallel
Updated Doneness for Design
CTAS Process
Daily FACT Deletes
ETL4 performance tuning
Daily Load Restructuring
Z
Doneness Created
Additional Requirements
Achieve 95% Utilization
East BI/PO
DW Archived
West MR/PR
Mart Archived
Create CCR
Z
Design
WV Vs NY Code Generation
Analysis WV
Implementation
Design
(DC,MD)
System Testing
Issue Resolution & Fix
Deploy
Analysis DC,MD
MD,DC Code Generation
VA Code Generation
Analysis VA
11/18 OOM for VA
Z
12/03
Production Release WV,MD,DC
11/30
Go/No-Go decision for WV,MD,DC
File Archiving
ASCII/Raw Files Archived
New Req Live
Reduce monthly PR process by 6-10 hours
and daily by 1 hr
Reduce MR monthly ETL4 by 3 hours and dailies by 1hr
Verizon uses trending report
ICS domain responsibilities completed
Estimate for Implementation Done
Validation of PAD VRepair Conversion
IView Conversion complete
USS drop
USS drop
USS drop
USS drop
West PO/INT
STG/DW/ Mart Archived
East BI/PO
DW Archived
12/03
Production Release WV,MD,DC
11/30
Go/No-Go decision for WV,MD,DC
Reduce monthly PR process by 6-10 hours
and daily by 1 hr
Reduce MR monthly ETL4 by 3 hours and dailies by 1hr
Cutover Night
Live
Phase III Req Complete
DB cleanup tasks identified
DB cleanup tasks identified
ICS domain responsibilities completed
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
System Testing
(All Domains)
POC
Z
Eval copy of 7.5 installed, environment configured
Code and configuration changes
(All Domains)
Upgrade Dev Env
Code & config changes complete
System test complete
Finalize deployment strategy
(All Domains) upgraded and live
M Ops Deliverables (VDSI - Chennai)
M Ops Deliverables (VDSI - Delhi)
D / W Ops Deliverables (VDSI team - Chennai)
D / W Ops Deliverables (Sapient team)
D / W Ops Deliverables (VDSI team - Delhi)
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
East CP Vrepair Design, Development, IT Testing, UAT
10659 Design (I&M,National OPS)
Oracle Upgrade Investigation & Requirements
Z
LOE complete
Z
Plan Complete &
Capacity Allocated
Planning & Scheduling
Informatica Upgrade Investigation & Requirements
Z
LOE complete
Planning & Scheduling
USS drop CP (troubles only)
USS drop iView (CP)
Vrep and NY,NE,NJ,VA,WV cleanup, analysis - Design, Dev, IT Testing, UAT
Static data update for PA,DE and analysis CP
Static data update and analysis PADE
USS drop Vrepair
(all regions)
Static data drop
Start Production Support
CP conversion complete
iView and NY,NE,NJ,VA,WV cleanup, analysis Design, Dev, IT Testing, UAT
USS drop iView
(all regions)
East iView for CP Design, Development, IT Testing, UAT
Release IV
Development Complete
Requirements/Design Complete
r
Plan Complete &
Capacity Allocated
Disk Space Allocation and STE Environment Setup
(Infrastructure Team - Frank Estremera)
Z
STE Environment Setup and Space Allocated
STE Environment Data Load and Configuration
Deployment Testing beginning with October Data Month Release
UAT
(All Domains)
Parallel
(All Domains)
Implement CCRs
(All Domains)
Prod Upgrade / Sniff Test
(All Domains)
System Testing
(East MR & PR)
Upgrade Dev Env
(East MR & PR)
Parallel
(East MR & PR)
Implement CCRs
(East MR & PR)
Prod Upgrade / Sniff Test
(East MR & PR)
UAT & Parallel complete
UAT & Parallel complete
Finalize deployment strategy
(East MR & PR) Upgraded and live
System test complete
Performance Testing beginning with October Data Month Release
MR/PR Performance (Contention) Investigation & Requirements
Z
LOE complete
Z
Capacity Allocated and Scheduled
Planning & Scheduling
Z
Plan Complete
PR Performance (CTAS) Investigation & Requirements
Z
LOE complete
Z
Capacity Allocated and Scheduled
Planning & Scheduling
DB cleanup tasks identified
USS drop
Phase I
EMR, EBI, WNP/CO/DU
Common Services
Database Archiving, File Archiving, File Management
Phase II
EPO, EOR, WOR, WMR, WPO/INT, WPR, WBI
Phase III
EPR, EASR, ENP/GE/OD, EOR
Execute - Source File archiving
(ongoing)
DM, FM Phase I Live
DW Phase I Live
STE Env. Ready
Phase II Live
DM, FM Phase III Live
DW Phase III Live
Req Closed with Infra team
Phase III Dev Complete
Phase III Design Complete
Phase II Dev Complete
Phase II Design Complete
Phase II Req Complete
Phase I Dev Complete
Phase I Design Complete
Phase I Req Complete
Verizon Checkpoint
Documentation Updates
Internal Review
Second Review
Final Review and Productionize
r
r
r
r
Z
Investigation & requirements complete
Z
STE Environment plan and capacity allocation complete
OR Performance (CTAS) Investigation & Requirements
Z
LOE complete
Z
Capacity Allocated and Scheduled
Planning & Scheduling
Live (09/17)
Development - I&M
IT Testing - I&M
Depl Testing - I&M
Finish matching for one month data
Development complete for I&M
USS drop for I&M
Development - National OPS
IT - Nat. OPs
Depl - Nat. Ops
Development complete for National OPS
USS drop for National OPS
Finish matching for one month data
Ramp up
Requirements Gathering
Design
Estimate for Implementation Done
Monitor Trending Results
Z
Final Metric Trending Templates
Create and test New users and disable old users on DEV
MSTR UID Cleanup complete
Z
Z
Z
MSTR UID Cleanup on DEV complete
Phase 1 Design
Phase 1 Implementation
Phase 1 Testing
Phase 2 Design
Prod. Cleanup
MSTR UID Cleanup on Prod. complete
Create New Users on NT1 and NT3 machines and disable old users
Static Data Drop
Validation of PAD VRepair Conversion
IView Conversion complete
October
DB cleanup tasks identified
DB cleanup tasks identified
Execute - File Archiving
Execute DB Archiving - EMR, EBI, WBI, EPO, EPR, WMR, WPR
Source Files Archived
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
USS drop
ASCII/Raw Data Files Archived
West BI
STG/DW/Mart Archived
DB cleanup tasks identified
DB cleanup tasks identified
East BI / PO
STG/Mart Archived
East MR/PR
Mart Archived
West PO/INT
STG/DW/ Mart Archived
Parallel
Updated Doneness for Design
CTAS Process
Daily FACT Deletes
ETL4 performance tuning
Daily Load Restructuring
Z
Doneness Created
Additional Requirements
Achieve 95% Utilization
East BI/PO
DW Archived
West MR/PR
Mart Archived
Create CCR
Z
Design
WV Vs NY Code Generation
Analysis WV
Implementation
Design
(DC,MD)
System Testing
Issue Resolution & Fix
Deploy
Analysis DC,MD
MD,DC Code Generation
VA Code Generation
Analysis VA
11/18 OOM for VA
Z
12/03
Production Release WV,MD,DC
11/30
Go/No-Go decision for WV,MD,DC
File Archiving
ASCII/Raw Files Archived
New Req Live
Reduce monthly PR process by 6-10 hours
and daily by 1 hr
Reduce MR monthly ETL4 by 3 hours and dailies by 1hr
Verizon uses trending report
Cutover Night
Gemini MD1 Installation in S1
Dress Rehearsal 1 Complete
Live
Creation of Release Documenatation
1st Draft Release Documenation
Complete and sent to VIS
VIS Review Time
Document Walkthrough
Updates to Release Documentation
VIS Review Time
Document Walkthrough
Release Documenation Accepted
Regression Test of Gemini MD1 in S1
Import of Production Product Catalogue and Content into S1
WRP Deploy to S1
Dress Rehearsal 1
Dress Rehearsal Testing
Dress Rehearsal 1
Regress to R3.1.0.4
Test
Gemini MD1 Regression test successful
Key Milestone: FAT & UAT Signoff
Key Milestone: Performance Signoff
Dress Rehearsal Build Delivered to VIS
Testing Signoff on Dress Rehearsal 1
Dress Rehearsal 2
Revision to Release Docs (if neccesary)
Revised Release Documentation Delivered to VIS
Dress Rehearsal Testing
Dress Rehearsal 2
Deploy to Primary
Drain & Cutover
Testing Signoff on Dress Rehearsal 3
ICS domain responsibilities completed
Estimate for Implementation Done
Validation of PAD VRepair Conversion
IView Conversion complete
USS drop
USS drop
USS drop
USS drop
West PO/INT
STG/DW/ Mart Archived
East BI/PO
DW Archived
12/03
Production Release WV,MD,DC
11/30
Go/No-Go decision for WV,MD,DC
Reduce monthly PR process by 6-10 hours
and daily by 1 hr
Reduce MR monthly ETL4 by 3 hours and dailies by 1hr
CPF Starts
CPF Ends
Cutover Night
(see later tab)
Pre-Cutover
Primary Install
Prod Cat and Content Updated in Staging for DR 1
Go-No Go for Deployment to Staging
VIS Review Time
Document Walkthrough
Release Documenation Accepted (DR 2)
Passive Support of MD1 Regression Test
ICS domain responsibilities completed
Estimate for Implementation Done
Validation of PAD VRepair Conversion
IView Conversion complete
USS drop
USS drop
USS drop
USS drop
West PO/INT
STG/DW/ Mart Archived
East BI/PO
DW Archived
12/03
Production Release WV,MD,DC
11/30
Go/No-Go decision for WV,MD,DC
Reduce monthly PR process by 6-10 hours
and daily by 1 hr
Reduce MR monthly ETL4 by 3 hours and dailies by 1hr
Disaster Recovery Install and Test
Tibco Deploy to S1
WRP Deploy to S1
Golden build available
Final CAB Meeting
#
#
DCAB meeting (11am)
5:30 PM - all test certs granted
PAYT Testing Completes
PAYT Test Environment Available
WRP Regress
Dress Rehearsal 3
WRP Deploy to S1

## SBM Plan (6-June Live Date) (hidden)
Vodafone CO.UK ¦ Release 4.0 (SBM) ¦ Mid Level Plan
|  |  |  | Week 6 |  |  |  |  | Week 5 |  |  |  |  | Week 4 |  |  |  |  | Week 3 |  |  |  |  | Week 2 |  |  |  |  | Week 1 |  |  |  |  | Week 0 |  |  |  |  | Week (1) |  |  |  |  | Week (2)
|  |  |  | 2006-04-24 | 2006-04-11 | 2006-04-12 | 2006-04-13 | 2006-04-14 | 2006-05-01 | 2006-05-02 | 2006-05-03 | 2006-05-04 | 2006-05-05 | 2006-05-08 | 2006-05-09 | 2006-05-10 | 2006-05-11 | 2006-05-12 | 2006-05-15 | 2006-05-16 | 2006-05-17 | 2006-05-18 | 2006-05-19 | 2006-05-22 | 2006-05-23 | 2006-05-24 | 2006-05-25 | 2006-05-26 | 2006-05-29 | 2006-05-30 | 2006-05-31 | 2006-06-01 | 2006-06-02 | 2006-06-05 | 2006-06-06 | 2006-06-07 | 2006-06-08 | 2006-06-09 | 2006-06-12 | 2006-06-13 | 2006-06-14 | 2006-06-15 | 2006-06-16 | 2006-06-19 | 2006-06-20 | 2006-06-21 | 2006-06-22 | 2006-06-23
| SBM Implementation | High Level Plan | Project Schedule
Implem. Schedule
Planning & Setup
Staging Environment Setup
Dress Rehearsal Schedule & Prep
Data Migration
Content Freeze
Implementation Management Team
| Implementation Mgmt Team Tracks | Testing
Clarify
CO.UK
CRP
Middleware & Tibco
Implementation Management Team
Formulas:
Week 5 = [Week 6]+7
Week 4 = [Week 5]+7
Week 3 = [Week 4]+7
Week 2 = [Week 3]+7
Week 1 = [Week 2]+7
Week 0 = [Week 1]+7
Week (1) = [Week 0]+7
Week (2) = [Week (1)]+7
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
Final Milestones
Interim Milestones
Vodafone Checkpoint
TBD
UK Bank Holiday
Implementation Management Activities (SBM Release)
Soft CMS & Product Catalogue Freeze
(Changes to impacted areas communicated to SBM Implementation Mgmt team)
UK Bank Holiday
German Bank Holiday
Dress Rehearsal 1
Dress Rehearsal 2
Implementation Planning & Preparation
Dress Rehearsal 1
SBM UAT/Functional Testing
SBM Performance Testing
Performance Signoff
Golden Build
FAT & UAT Signoff
Cutover
Post Deployment Activities
Import of CMS/Prod Cat Data
Staging Env Testing
CMS/PC Export
S1 Import Complete
S1 Import Complete
S1 Environment Certified
S1 Env BAU & Version Analysis
S1 Data Setup
(Data Migration)
Hard CMS & Product Catalogue Freeze
(No Changes to SBM impacted Content or Product Cat Data)
Hard Freeze Starts
Soft Freeze Starts
Cutover
Test
Regress
Cutover
Test
Data Migration Testing in T3
Dress Rehearsal 2
Cutover Week
Cycle 1
Cycle 2
Cycle 3 (Dress Rehearsal)
Cycle 4 (DR2)
Build Release Package
Draft of Release Package to VIS
VIS Review
VIS Review 1
VIS Review
VIS Review 3
Update Package
Final Updates
Release Package Closed for DR1
Update Package
VIS Review
Release Package Closed for DR2
Test Certificate Complete
Go-No Go Decision
Live
SBM Performance Testing Preparation
Deployment Test Preparations & Planning
Sniff Test of S1
(Pre DR1)
DR 1 Testing
DR 2 Testing
Cutover Testing
S1 Data Req. Analysis & Setup
Setup of Staging Environment
Dress Rehearsal 1 Complete
Dress Rehearsal 2 Complete
Test Approach and Script Review
Environment Certified and Test Approach/Scripts closed for DR1
Test Prep (DR2)
Test Prep (P1)
Test Prep Complete (DR2)
Test Prep Complete (Prod)
Low Level Cutover Plan Creation (TBC)
Draft of LLP for Cutover to Implementation Mgmt team
DR 1 Deployment & Support
Regress & Support
Revisions to Deployment Plan
DR 1 Deployment & Support
VIS Review 2
Production Deployment & Support
Prod Deployment Plan
Prod Deployment Plan final (DR2)
Deployment LLP Closed for DR2
Golden Build Complete
Deployment LLP Closed for DR1
Build Identified for DR1
Low Level Cutover Plan Creation (TBC)
DR 1 Deployment & Support
Regress & Support
Revisions to Deployment Plan
DR 1 Deployment & Support
Production Deployment & Support
Prod Deployment Plan
Prod Deployment Plan final (DR2)
Deployment LLP Closed for DR2
Golden Build Complete
Deployment LLP Closed for DR1
Build Identified for DR1
Low Level Cutover Plan Creation (TBC)
DR 1 Deployment & Support
Regress & Support
Revisions to Deployment Plan
DR 1 Deployment & Support
Production Deployment & Support
Prod Deployment Plan
Prod Deployment Plan final (DR2)
Deployment LLP Closed for DR2
Golden Build Complete
Deployment LLP Closed for DR1
Build Identified for DR1
Staging CMS/Prod CatSync
Build Identified for DR1
Golden Build Complete
VIS Review
Update Package
Release Package Closed for Production
Production Deployment & Support
Dress Rehearsal 1
Dress Rehearsal 2
Draft Comunication Plan
Communication Plan Complete
Support Teams and Coverage Closed
Production Test Data Setup
Mirror Environments Verified (S1, T1, T0)

## workplan
S. No. | Task | Owner | Start | Due | Comments | Status
1. | Proposal Development/ Phase 1 Strategy
1.1 | Phase 1 Scope & Functionality
1.1.1. | Customer Base Management | Rosh/Rob | 2011-10-24 | 2011-10-26
1.1.2. | Campaign Management Integration | Barry | 2011-10-24 | 2011-10-27
1.2. | Phase 1 Solution Architecture
1.2.1. | Phase 1 Solution Architecture | Joe | 2011-10-24 | 2011-10-27
1.2.2. | Software/Hardware Costs & Assumptions | Joe | 2011-10-24 | 2011-10-27
1.3. | Team Organization
1.3.1 | SERVE Resource Requirements | Rob | 2011-10-24 | 2011-10-27
1.3.2 | Vistrada Resource Requirements | Rob | 2011-10-24 | 2011-10-27
1.3.3 | Caserta Resource Requirements | Joe | 2011-10-24 | 2011-10-27
1.4. | Additional Proposal Development
1.4.1. | Overview & Background | Rob | 2011-10-24 | 2011-10-27
1.4.2. | Current State | Rob | 2011-10-24 | 2011-10-27
1.4.3. | Timeline | Rob | 2011-10-24 | 2011-10-27
1.4.4. | Approach | Rob | 2011-10-24 | 2011-10-27
1.4.5. | Fees | Rob | 2011-10-24 | 2011-10-27
2 | Key Source Meetings
2.1.1 | Proposal Kickoff Meeting | Rosh/Rob | 2011-10-26 | 2011-10-26
2.1.2 | Campaign Management Integration with Dell/Barry | Rob | 2011-10-26 | 2011-10-27
2.1.3 | Solution Approach Review with Mike Anderson | Rob | 2011-10-27 | 2011-10-28
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
No Service Impact
Release Outage Window Begins
Full Site Holding Page
Holding Page Up:
Start Deployment
Release on Preview Cluster (2 hrs)
CPF Ends
Regression Timeline
(6 hours = 5 hours regress + 1 hour test)
Go/No Go Decision for Live
Take decision on plan forward
Inform support teams
No Service Impact
Post-Deployment Testing (4 Hr)
Full Site Holding Page Up
Live: Holding Page down
Cutover to Live
(2 hours)
Deployment Complete: Ready for Testing
CRP Deployment Started
Cutover Readiness Checkpoint
Begin Cutover Activities: Holding Page
Go No-Go Decision
for Regression
Post-Cutover Activities (5 hr)
Milestones
Go/No-Go Meetings
Key Communication Point
Dependencies Dependencies
Begin Cutover to Live:
Set Live Expectations
1st Go No-Decision for Live: 12:30 PM
Hourly Checkpoints with Business
Implementation Activities Complete
2nd Go No-Decision for Live: 2:00 PM
Release TOL 2.0 Live
Restart Secondary in Debug mode (45 min)
Partial Holding page up (15 min)
CMS Release
(1.5 hrs)
Support of Testing Activities
Clarify Deployment Started
Clarify Deployment Complete
Buffer
Contingency (4.5 hours)
Support of Testing Activities
No Outage Deployment Activities (7 hours)
Deployment Complete:
Testing Begin
Outage Activities (3 hr)
Web Release on
LIVE (45 min)
Bank wizard (30 min)
Check Point
No Service Impact
Post-Live Testing
Post-Live Testing
Backups(30 min)
Clarify Deployment
(60 min)
Drain Sessions from Primary to Secondary (30 min)
Restart Secondary (45 min)
Bring Down Partial Holding page (15 min)
q
Hourly Updates
1st Deployment complete,
Full holding page up.
Release TOL 2.0 Live. Start post live testing testing
WEB + Stakeholders + Release Team - Wrap up call, hand over to support
Inform NI - IT send other relevant teams

## Low Level (Cutover Night Draft) (hidden)
Vodafone 4.0 Release ¦ Cutover Night Low Level Plan
|  |  | Monday, June 12 | [6 empty] | Tuesday, June 13 | [23 empty] | Wednesday, June 14 | [23 empty] | Thursday
|  | GMT | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM
|  | IST | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-1.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-1.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5
|  | Germany | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM
Overall Schedule (CPF Milestones)
Key Communication Points
CRP Activities
| Data Migration Activities | CRP Activities
CO.UK Activities
TIL Activities
CO.UK Activities
Middleware Activities
Clarify Activities
Testing Activities
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
Partial Site Holding Page
Rollback Path: Bring up complete site holding page
Restore previous CMS and Db , release,Bring down secondary cluster, Restart primary with backed up config.xml and queue's deployed. Point preview web server to primary and perform testing
Deployment to Primary cluster and restart of cluster
Release App on Secondary
Primary & Secondary Weblogic Instance Backup
Preview Weblogic Instance Backup
Point Preview Webserver to Secondary
DB Release & Restart
Restart Secondary Cluster and Drain Sessions from Primary (R3.1.1 is live to public behind holding page)
Support of Testing Activities
DB Export
Web Server BackUP
Web Release on Secondary
CPF Outage Window Begins
No Service Impact
Full Site Holding Page
Pre-CPF Activities
(2 hours)
Validate Full Site Holding Page
Holding Page Up: Start Deployment
Validate PartialHolding Page
Sniff Test
Test Pre-3.1.1 functionality
Test Post-3.1.1 functionality
Bring down holding page
Release on Preview Cluster
Point Preview Webserver to Primary
Support of Sniff Testing Activities
Drain Sessions from Secondary to primary
CPF Ends
Regression Timeline
(6 hours = 5 hours regress + 1 hour test)
Go Decision for Live
Validate Holding Page Down
Post-Live Testing
Pot-Live Sniff Testing on Primary Cluster
No Service Impact
Outage Deployment Activities
(3.5 hours)
Post-Deployment Testing
(4 hours)
Full Site Holding Page Up
Partial Site Holding Page Up
Live: Holding Page down
Cutover to Live
(2 hours)
Testing Complete: Ready for Live
Hourly Status Updates
Deployment Complete: Ready for Testing
CRP Deployment Started
Full Holding Page Validated
Partial Holding Page Validated
Sniff Test Successful
Regression Testing Successful
Release 3.1.1 functionality validated
Testing Complete
Holding Page Down
Post Live Testing Complete
Sniff Testing on Primary Cluster Complete
Pointing of Preview Webserver at Preview
Cutover Readiness Checkpoint
Cutover Readiness Checkpoint
Begin Cutover Activities: Holding Page
Go No-Go Decision for Regression
Post-Cutover Activities
(6 hours)
Milestones
Go/No-Go Meetings
Team Specific Communication Points
Implementation Dependencies
Begin Cutover to Live: Set Live Expectations
1st Go No-Decision for Live: 10:00 AM
Hourly Checkpoints with Business
Cutover Readiness Checkpoint
Post-Live Testing (Primary)
Post Drain Testing Complete on Primary
Sapient-VIS Checkpoint: 7:00 PM
Implementation Activities Complete
Partial Site Holding Page
Partial Site Holding Page Up
Tibco Release
(~ 2 hrs: TBC)
Support of Testing Activities
Tibco Deployment Started
2nd Go No-Decision for Live: 1:30 PM
Release 4.0 Live
Export Complete & Sent to CO.UK
CRP DB Backup
CRP Export Validation (2 hr)
CRP Export Received by CO.UK
TIL BAN Lookup
File Sent to TIL for BAN Lookup
File Received from CO.UK for BAN Lookup
Marketing Data Cleansing
(3 hr)
CRP Export Validated Successfully?
Other CO.UK
Migration
CO.UK CRP Data Import
File Sent to CO.UK w/ BAN Lookup Data
Restart Secondary in Debug mode
PartialHolding page up
CMS Release & Restart
Put up Site Holding Page
Verity Release
Put up Site Holding Page
Tibco Deployment Complete
Clarify Release
(~ 2 hrs: TBC)
Support of Testing Activities
Clarify Deployment Started
Calrify Deployment Complete
Validate Partial Site Holding Page
Buffer
(1 hr)
Contingency
(6 hours)
Support of Testing Activities
CRP Data Cleansing
CRP Configuration Changes
CRP Config Changes Started
CRP Config Changes Complete
Partial Outage Deployment Activities (3.5 hours)
Data Migration Activities
(6.5 hours)
Deployment Complete: Testing Begin

## Resources (hidden)
Vodafone 4.0 SBM Release ¦ Cutover Night Coverage Plan
|  |  |  | Monday, June 5 | [6 empty] | Tuesday | [23 empty] | Thursday | [23 empty] | Wednesday
|  | GMT |  | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM
|  | IST |  | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-1.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 1.5-1.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5
|  | Germany |  | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM | 1-2 AM | 2-3 AM | 3-4 AM | 4-5 AM | 5-6 AM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 9-10 PM | 10-11 PM | 11-12 PM | 12-1 AM
Implementation Management
WRP
Vis Germany | bar: 7-8 PM to 5-6 PM
Infra India | bar: 7-8 PM to 5-6 PM
Functional Support India | bar: 1-2 AM to 5-6 PM
Middleware
Middleware Team | bar: 10-11 PM to 5-6 PM
Dave Smitham | bar: 5-6 AM to 12- 1 PM
Ed Arthur | bar: 11-12 PM to 11-12 AM
Problem Resolution
Pinak Vedalankar | bar: 2-3 AM to 2-3 PM
Kevin Lee | bar: 6-7 AM to 4-5 PM
Tommy Doyle | bar: 7-8 AM to 5-6 PM
Matt Haith | bar: 3-4 AM to 12- 1 PM
Webservices
James Richards | bar: 5-6 AM to 3-4 PM
Colin Bateman | bar: 5-6 AM to 4-5 PM
Richard Down | bar: 8-9 AM to 1-2 PM
|  |  | Sam Morrison (Hols) | 6-7 PM: Unavailable
Darren Morgan | bar: 10-11 AM to 6-7 PM
Business/Programme
Helen Dalley | bar: 5-6 AM to 4-5 PM
Dave Newton | bar: 7-8 AM to 5-6 PM
Testing
Donna Matthews | bar: 3-4 AM to 12- 1 PM
Ramesh | bar: 2-3 AM to 12- 1 PM
Test Team (A) | bar: 2-3 AM to 10-11 AM
Test Team (B) | bar: 10-11 AM to 6-7 PM
Test Lead (B) | bar: 10-11 AM to 6-7 PM
Paul Warner (UAT) | bar: 4-5 AM to 2-3 PM
On Call
Mark Diamond | bar: 11-12 PM to 9-10 AM
Clarify | bar: 2-3 AM to 6-7 PM
CRP | bar: 2-3 AM to 6-7 PM
Ufulfil | bar: 2-3 AM to 6-7 PM
Gemini | bar: 2-3 AM to 6-7 PM
Transact?Solve SE | bar: 2-3 AM to 6-7 PM
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified

## Contacts (hidden)
Role | Name | Phone Number
Architects
| Ed Fletcher | +447766028738
API/Tuxedo
Amdocs - See Gemini Support
BDS - UTB
| Matt Innes | +447977415773
CRP
Andy Pedgley | MACS Network Services | 07000 975312 | 24 x 7 | 24 x 7
DBA
Support (76535) | for eCRM Clarify | 76535 | 24 x 7 | 24 x 7
Environments
| Mark Diamond (Gemini) | +447760170264 | Mobile | Office Hours
| Matthew Haith | +447768052477 | Mobile | Office Hours
7 x 24 Production | Incident Management | 77788 | 24 x 7 | 24 x 7
Middleware
| Chris Viney | 07919 994 647
| Group Number | +447000 24 24 24 | Office Hours | Office Hours
Sapient Management - UK | Jason Ferreri | +447810662136
| Khaja Mohideen | 00919899787855
SolveSE
| Rhona Shaw | +447776465590 | Mobile | Mobile
Testing
| Ramesh Ranganatha | +447717512232
Tibco
| Ed Arthur | +447967687178
| Dave Smitham | +447980280614
| Support | +447785388997 | 24 x 7 | 24 x 7
eCRM Clarify
Support | Kiran Mandra | +447899013987
Transact
| John McLauchlan | +447717274763
Ufulfil | HelpDesk | 01865384333
Ufulfil dedicated IT Support | Mike Bowtell | 07979 134073
Ufulfil Warehouse | Chris Collins or Lee Fawcett | 02476 21 7812 |  | From 06:00
Unix
Production | Ops incident management | 76535 / 76545
Web Services
| Julian Moss | +447771800760 | Theale | Theale
| Richard Down | +447786250254 | Theale | Office Hours
| James Richards | +447879445216 | Theale | Office Hours
Escalation Points:
Vodafone Helpdesk - UK | url for all numbers = http://uki/general/numbers.asp | 08454 420304 | For problems with Network, Unix, Test Director, etc. Note that calls will automatically be transferred to the Incident Centre for out of hours support
Vodafone Helpdesk - India |  | +441635667123
Helpdesk Hours |  |  | Normal Hours: Mon-Sun 07:00 - 22:01 | Out of Hours: Mon-Sun 22:00 - 07:00
Test Director (Hardware) | Leonie Leigh | +447766775796 | For problems restarting TD server, call Helpdesk First
TIBCO | Dave Smitham | +447980280614
Gemini | Production Support Gemini Ops | +441635 664464
CRP | Tom Hearn | +447747 008983
Webtrends | Phone Ramesh in first instance.
Project
Programme Manager | Dave Newton | +447717425181
R3.1.1 Project Manager | Alex Bowden | +447919555244
Implementation Lead | Jason Ferreri | +447810662136
Ops Lead | Russell Gronow | +447778777060
Release Lead | Colin Bateman | +447717432873
Problem Management | Nehad Elbaz | +447717512216
Online and Consumer Direct Sales | Helen Dalley | +447884313581
Conference Call No | 0870 111 8201 Pin 443111
Located in Theale = | Refer to Resource Plan

## Dress Rehearsal 1 (hidden)
Vodafone 3.1.1 Release ¦ Dress Rehearsal 1 Schedule
|  |  | Tuesday | [7 empty] | Wednesday | [13 empty] | Thursday | [13 empty] | Monday
|  | GMT | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 6-7 AM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM
|  | IST | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5 | 11.5-12.5 | 12.5-1.5 | 1.5-2.5 | 2.5-3.5 | 3.5-4.5 | 4.5-5.5 | 5.5-6.5 | 6.5-7.5 | 7.5-8.5 | 8.5-9.5 | 9.5-10.5 | 10.5-11.5 | 11.5-12.5 | 12.5-1.5
|  | Germany | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM | 7-8 AM | 8-9 AM | 9-10 AM | 10-11 AM | 11-12 AM | 12- 1 PM | 1-2 PM | 2-3 PM | 3-4 PM | 4-5 PM | 5-6 PM | 6-7 PM | 7-8 PM | 8-9 PM
Overall Schedule
Key Communication Points
WRP Activities
Middleware Activities
CRP Activities (None in DR1)
Testing Activities
Communications
1 | Pre-Cutover Activities Started |  | x
2 | Pre-Cutover Activities Complete: Bring up Holding Page |  | x
3 | Holding Page Up: Start Deployment |  | x
4 | Deployment Complete: Testing Kickoff |  | x
5 | Testing Complete: |  | x
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
Full Site Holding Page
Release App on Secondary
Primary & Secondary Weblogic Instance Backup
Preview Weblogic Instance Backup
Point Preview Webserver to Secondary
DB Release & Restart
Support of Testing Activities
Put up Site Holding Page (shutdown primary)
CMS Release & Restart
Restart Secondary in Debug mode & Primary with queues undeployed
PartialHolding page up
Db back up
Web Server BackUP
Web Release on Secondary
Tibco Release
(Upgrade Engines & Update DB)
No Service Impact
Partial Site Holding Page
Pre - Cutover Activities
(4 hours)
Validate Full Site Holding Page
Holding Page Up: Start Deployment
Deployment Complete: Testing Begin
Support of Testing Activities
Support of Testing Activities
Validate Partial Site Holding Page
Sniff Test
Test Pre-3.1.1 functionality
Test Pre-3.1.1 functionality
Go Decision for Regression
Testing Continues (if necessary)
Deployment Activities
(4 hours)
Post-Deployment Testing
Full Site Holding Page Up
Partial Site Holding Page Up
Signoff on Dress Rehearsal
Cutover to Live
(2 hours)
Tibco Deployment Complete
Tibco Deployment Started
Full Holding Page Validated
Partial Holding Page Validated
Sniff Test Successful
Dress Rehearsal Walkthrough
Begin Cutover Activities: Holding Page
Regress to R3.1.0.3
(5 hours)
Milestones
Go/No-Go Meetings
Team Specific Communication Points
Implementation Communication Points
Dress Rehearsal Complete: Regress in AM
Post-Deployment Testing
S1 Environment Preparation
S1 Sniff Testing
Staging Validated Pre-Release
Testing of Regression
Holding Page up: Begin Regression Activities
Regression Activities Complete: Beging Testing
Regression Verified: Dress Rehearsal 1 Complete
Dress Rehearsal Checkpoint
Dress Rehearsal Checkpoint
DR 1 Debrief
Rollback Path: Bring up complete site holding page
Restore previous CMS and Db , release,Bring down secondary cluster, Restart primary with backed up config.xml and queue's deployed. Point preview web server to primary and perform testing
Support of Testing Activities
Support of Testing Activities
Stging Sniff Test
Testing of R3.1.0.3 Regression
Regress Tibco
Support of Testing Activities
Support of Testing Activities
Deployment Activities Complete

## Cutover Night Schedule (hidden)
Vodafone WRP ¦ Release 3.1.1 ¦ Cutover Night Schedule
Week 0
| Vodafone WRP Release 3.1.1 |  |  | Saturday (11-Mar) |  |  |  | Sunday (12-Mar) |  |  |  | Monday (13-Mar) | [5 empty] | Tuesday (14-Mar) | [11 empty] | Wednesday (15-Mar) |  |  |  | Thursday (16-Mar)
|  |  | GMT | 6-9 AM | 9-12 AM | 12-3 PM | 3-6 PM | 6-9 AM | 9-12 AM | 12-3 PM | 3-6 PM | 12-6 AM | 6-12 AM | 12-6 PM | 6-8 PM | 8-10 PM | 10-12 PM | 12-2 AM | 2-4 AM | 4-6 AM | 6-8 AM | 8-10 AM | 10-12 AM | 12-2 PM | 2-4 PM | 4-6 PM | 6-8 PM | 8-10 PM | 10-12 PM | 12-6 AM | 6-12 AM | 12-6 PM | 6-12 PM | 12-6 AM | 6-12 AM | 12-6 PM | 6-12 PM
|  |  | CET | 7-10 AM | 10-1 PM | 1-4 PM | 4-7 PM | 7-10 AM | 10-1 PM | 1-4 PM | 4-7 PM
|  |  | IST | 11.5-2.5 PM | 2.5-5.5 PM | 5.5-8.5 PM | 8.5-11.5 PM | 11.5-2.5 PM | 2.5-5.5 PM | 5.5-8.5 PM | 8.5-11.5 PM | 5.5-11.5 AM | 11.5-5.5 PM | 5.5-11.5 PM | 11.5-1.5 AM | 1.5-3.5 AM | 3.5-5.5 AM | 5.5-7.5 AM | 7.5-9.5 AM | 9.5-11.5 AM | 11.5-1.5 PM | 1.5-3.5 PM | 3.5-5.5 PM | 5.5-7.5 PM | 7.5-9.5 PM | 9.5-11.5 PM | 11.5-1.5 AM | 1.5-3.5 AM | 3.5-5.5 AM | 5.5-11.5 AM | 11.5-5.5 PM | 5.5-11.5 PM | 11.5-5.5 AM | 5.5-11.5 AM | 11.5-5.5 PM | 5.5-11.5 PM | 11.5-5.5 AM
Cutover Night Plan (Tentative)
Option 1
Option 2
Option 3
Option
| Oversight | UK | Andrew
Jason
|  | India | Deepak
Bhaskar
Prashant
| Infrastructure |  | Wasim
Manav
Ashish
Sachin
| Support |  | Anurag
Amit
|  |  | Vivek | [26 empty] | Leave 6 AM
|  |  | Nishant | [26 empty] | Leave 6 AM
|  |  | Saurabh | [26 empty] | Leave 6 AM
Ankit
Aditya
| R 2.0 |  | Abhishek | [26 empty] | Leave 6 AM
Abhinav
|  |  | Sudhanshu | [26 empty] | Leave 6 AM
|  |  | Parag | [26 empty] | Leave 6 AM
Sunil
Rajiv
Rohit P.
Rohit M.
Coverage Schedule
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
DB cleanup tasks identified
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Milestone #2
Milestone #1
Milestone #2
Milestone #1
Milestone #2
Milestone #2
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Milestone #3
Milestone #3
Milestone #3
Milestone #3
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Milestone #1
Milestone #1
Cutover
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
November R_Monthly Live
Package and Close
November R_01 Live
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Outage CPF Starts: 10 PM
Outage CPF Ends: 5 PM
Cutover Activities
RelQ Testing
Cont'd
Go-No Go Mtg: 8 AM
Live: Best Case
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Package and Close
Redeployment and Retest of WRP
Decision Point: Ready for Cutover? Additional deployment necessary?
Testing
Decision Point: Ready for Cutover?
CPF Starts: 5 PM
CPF Ends: 12 PM
Preview Deployment
Team 1 (5 PM to 4 AM)
Team 2 (2 AM to 1 PM)
Team 3 (12 Noon to 11 PM)
Pre-Cutover Activities
Cont'd
Deployment Complete: Best Case
Testing Complete
Final CutoverActivities
Final VIS Checkpoint
Cont'd
Primary Deploy & Drain